## Read Me
To use the template
0 | File -> Make a copy, and share it among the members & the instructor (yan.chen01@sjsu.edu)
1 | In Members, enter member names & email for each role
(for 3-people group, delete 1 row of programmer)
2 | In Backlog, enter group number (members will be auto-filled in based on what you entered in 1)
Then document each task as a row:
| 2.1) | Choose milestone number
| 2.2) | Describe the task (method name, class name, etc.)
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 1 & 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task

## Members
Role | Name | Email
UI Designer | Ayman Rabia | ayman.rabia@sjsu.edu
Programmer | Dima Gamolya | dima.gamolya@sjsu.edu
Programmer | Thang Cao | thang.cao02@sjsu.edu
Tester | Gloria Duo | gloria.duo@sjsu.edu

## Backlog
Group 8
Members: | Ayman Rabia, Dima Gamolya, Thang Cao, Gloria Duo
Milestone # | Task | Member | Status | Start Date | End Date | Comments
Milestone 2 | Implement occursOn | Thang Cao | Completed | 2024-10-09 | 2024-10-10
Milestone 2 | Test occursOn | Gloria Duo | Completed | 2024-10-09 | 2024-10-10